## Sheet1
FGDC Address Standard Review - Timeline
Submit committee draft to FGDC SWG | 2015-08-25
Present at FGDC SWG/recommend for Public Review | 2015-09-25
Submit to FGDC CG for approval for Public Review | 2015-10-01
Present at FGDC CG/endorse for Public Review | 2015-10-14
Public Review | October 15, 2015 - January 12, 2016
Adjudicate Comments | January 12, 2016 - January 31, 2016
Prepare Final Draft | February 1, 2016 - February 15, 2016
Submit to FGDC SWG | 2016-02-16
FGDC SWG endorses standard | 2016-03-18
Submit to FGDC CG | 2016-03-31
FGDC CG endorses standard | 2016-04-14
FGDC SC endorses standard | Next meeting after April 14, 2016