## Sheet1
Maintenance Review of the FGDC United States Thoroughfare, Landmark, and Postal Address Data Standard
FGDC Directive | Action | Dates
FGDC Directive #9, 3.3 | Initiate Work for Maintenance Review | 2013-09-01
FGDC Directive #9, 3.3 | Initial Maintenance Review Meeting | 2013-11-22
FGDC Directive #9, 3.3 | Complete Review Draft | 2014-05-31
FGDC Directive #1 Step 5 | GEO Review of revised standard; Submit to FGDC Standards WG for review - make recommendation to FGDC | 2014-06-30
FGDC Directive #1 Step 6 | Coordination Group - Approve Standard for Public Review | 2014-07-08
FGDC Directive #1 Step 7 | Coordinate Public Review | 2014-07-31
FGDC Directive #1 Step 8 | Coordinate Public Review - Federal Register Notice - send out notice | 2014-08-13
FGDC Directive #1 Step 8 | Coordinate Public Review - Federal Register Notice - notice deadline | 2014-11-29
FGDC Directive #1 Step 9 | Respond to public comments - Address WG evaluate responsiveness to public comments | 2015-01-30
FGDC Directive #1 Step 10 | FGDC Standards WG - review comments - make recommendation | 2015-02-28
FGDC Directive #1 Step 11 | Approval of Standard by FGDC Coordination Group | 2015-03-10
FGDC Directive #1 Step 12 | Endoresement of Standard by FGDC Steering Committee | 2015-04-10